## Sheet1
Product Backlog
| User | Task | Outcome | Sprint | Status
1 | College Student | see a list of universities with their distance from Saddleback College | On the Display Campuses page, user gets to see a list of campuses with their distance from Saddleback College | 1 | Completed
2 | College Student | purchase souvenirs from school campuses during the trip | User has the ability to purchase souvenirs from each campus on the trip (max of 7 souvenirs) | 1 | In progress
3 | Admin | add or delete colleges and souvenirs | Admin can add and delete college campuses as well as souvenirs from the Admin Settings Menu | 1 | Completed
4 | College Student | have a custom trip starting anywhere desired | User can have a college tour trip starting anywhere they desire, proceeding to the next closest campus each time | 2 | In progress
5 |  | have a trip planned out from ASU to the 13 closest universities | When ASU is clicked, user gets a trip planned starting from ASU to the nearest colleges respectively | 2 | To be started
7 | College Student | have a trip planned out from UCI to the 13 closest universities | When UCI is clicked, user gets a trip planned starting from UCI to the nearest colleges respectively | 2 | To be started
8 | College Student | see the total distance in miles for each trip | After the trip is done, user can see the total distance the trip took in miles | 2 | In progress
6 | College Student | start the trip at any campus desired | to plan a custom trip and decide what to visit next | 3 | To be started
9 | College Student | see the total amount that I will be spending on each souvenir | User gets to also see the total amount spent on souvenirs after the trip | 3 | To be started
10 | Admin | hold all of the most accurate information about all of the universities’ inventory | Admin can look at and modify all college information and their souvenirs | 3 | To be started
Team | Angry Nerdz
Team Members | Awf Wiswasi (Product Owner)
Meredith Seifoleslami (Scrum Master)
Amin Parvizi
Behrad Rezazadeh Moussavi